## Slide 1: Movie Recommender Lab: who does what
DS-311 Data Mining · Fall 2026 · Project P07
No lead roles. Each of us owns one recommender end to end: data slice, model, evaluation, app panel and report section.
MEMBER A · REPO OWNER
Data quality + content-based
MEMBER B · EMMAN
EDA + collaborative filtering
MEMBER C · ACHU
Evaluation + association rules

## Slide 2: The project in one picture
1
Get the data
Download MovieLens, join the tables, check and clean it.
A · Repo owner
→
2
Understand it
EDA: how sparse is it, which movies are popular, what do ratings look like?
B · Emman
→
3
Set up a fair test
Split past vs future, define the scores, build a simple baseline to beat.
C · Achu
→
4
Build 3 recommenders
One method each, all scored the same way.
A · content
B · CF
C · rules
→
5
Compare, show, explain
Comparison table, web app, report and viva.
All three
Everyone does one piece of steps 1–3, one recommender in step 4, and one part of step 5.

## Slide 3: Why we split it this way (no lead roles)
Course rule
Every member must build and name a mining technique. One recommender each covers that.
Fair credit
Each person commits their own notebooks and code, so GitHub shows real work from all three.
Easier viva
You explain what you built yourself; weekly walkthroughs prepare you for teammates’ parts.
Little waiting
Only two hand-offs: A’s data loader by 18 Oct and Achu’s test harness by 28 Oct. The rest runs in parallel.

## Slide 4: How we split the work
Everyone builds one recommender (the guide requires each member to implement a mining technique) plus one slice of the shared groundwork.
 | A · Repo owner | B · Emman | C · Achu
Shared groundwork | Data loading, joins, dictionary, data-quality report | EDA: sparsity, long tail, distributions, hypothesis test | Time-based split, metrics, popularity baseline
Own recommender | Content-based (TF-IDF + cosine) and cold-start | Collaborative filtering: kNN + SVD | Association rules on liked movies
Web app | Dashboard page | “Rate 5 movies” page | Deployment
Report section | Data | Pipeline & methods | Experiments & results
Together: insights, limitations, optional hybrid, slides and demo rehearsal

## Slide 5: Everyone, before Wed 14 Oct (M0)
GitHub
Repo structure is ready ✓ (folders, README, requirements, CLAUDE.md)
Member A (repo owner) adds Emman and Achu in Settings → Collaborators
Emman and Achu accept the invite and set git user.email to their own GitHub email
Each adds their row to the README contribution table, one at a time
Colab + proposal
Open notebooks from the GitHub tab in Colab
Save with File → Save a copy in GitHub: the commit is under your account
Each member makes one test commit
Write the 1-page proposal together: problem, 3 questions, module ownership split
Never commit MovieLens files: every notebook downloads them from GroupLens

## Slide 6: Member A · data & content-based
A
Shared groundwork
Load MovieLens in Colab; join ratings, movies, tags, links
Write the data dictionary
Data-quality report: missing, duplicates, bad values, outliers, each decision justified
Own recommender
TF-IDF on genres + tags, cosine similarity
“Because you liked…” explanation
Cold-start analysis for users with few ratings
Score it with Achu’s harness vs the baseline
App & report
Dashboard page with EDA charts
Report: Data section (source, license, cleaning)
Explain this module in the viva
FILES YOU OWN
01_data_quality_A.ipynb · 04_content_based_A.ipynb · src/data.py · src/content_based.py
DECISIONS YOU MAKE
How to sample the 32M data, how to treat outliers, which tags to keep, how to cite the dataset
Member A · repo owner

## Slide 7: Emman · EDA & collaborative filtering
B
Shared groundwork
Sparsity of the user–movie matrix
Long tail of popularity, rating distributions
At least one hypothesis test that answers a real question
Own recommender
Item-item and user-user kNN (cosine / Pearson)
Matrix factorisation with TruncatedSVD
Show the effect of k and n_components
RMSE + top-k metrics via Achu’s harness
App & report
“Rate 5 movies” page wiring all three recommenders
Report: Methods section + pipeline diagram
Explain this module in the viva
FILES YOU OWN
02_eda_B.ipynb · 05_collaborative_B.ipynb · src/collaborative.py · app/app.py (try-it page)
DECISIONS YOU MAKE
Which hypothesis test, which k and n_components, how to keep the matrix small enough for Colab
Member B · Emman

## Slide 8: Achu · evaluation & association rules
C
Shared groundwork
Time-based train/test split per user + leakage check
RMSE, precision@k, recall@k, NDCG
Popularity baseline everyone compares against
Own recommender
Rules on “liked” movies (rating ≥ 4)
FP-Growth in mlxtend; tune support, confidence, lift
Rule-based “because you liked” explanation
Final comparison table of all methods
App & report
Deploy on Streamlit Community Cloud
Report: Experiments & results section
Explain this module in the viva
FILES YOU OWN
03_evaluation_baseline_C.ipynb · 06_assoc_rules_C.ipynb · src/evaluation.py · src/assoc_rules.py
DECISIONS YOU MAKE
The train/test cutoff, what counts as “liked”, k for top-k lists, support and confidence thresholds
Member C · Achu

## Slide 9: What each of us shows at every milestone
Milestone | A · Repo owner | B · Emman | C · Achu
M0 · 14 Oct | Repo + invites done; data loads in Colab ✓ | Proposal draft: 3 questions | Accept invite, first commit, evaluation plan for the proposal
M1 · 21 Oct | Data-quality report + dictionary | EDA + hypothesis test | Time split + metrics harness
M2 · 28 Oct | Content-based v1 | Item-kNN v1 | Popularity baseline + first rules
M3 · 18 Nov | Cold-start analysis; dashboard page | User-kNN + SVD; try-it page | Rules recommender; app skeleton runs
M4 · 2 Dec | Evaluated and tuned | Evaluated and tuned | Comparison table; app at public link
Wk 15–16, together: insights, limitations, optional hybrid, report, full demo dry-run.

## Slide 10: Six team rules
Own your notebooks
Never edit a teammate’s .ipynb at the same time.
Pull, then push
git pull before work; small commits from your own account.
No data in the repo
Download MovieLens in Colab; data/ stays in .gitignore.
One interface
Every recommender has fit() and recommend(); Achu’s harness scores all of them.
Weekly walkthrough
20 minutes each; the viva asks about teammates’ modules too.
Disclose AI use
Log Claude Code use in the report and be able to explain every line.